# Narrative Justification — Health Outreach

## Overview

This narrative summarizes progress against KPIs for the reporting period **2025-10-01 to 2025-12-31**.

## Results against KPIs

### 1. Clinics supported

Target: 12; Actual: 11

Measurement: Facility support logs + signed checklists

Evidence summary: Evidence found in kpi_sheet.csv, facility_support_checklists.docx supporting measurement: Facility support logs + signed checklists.

Key sources: kpi_sheet.csv, facility_support_checklists.docx

### 2. Households visited

Target: 1500; Actual: 1420

Measurement: Field visit forms + supervisor summaries

Evidence summary: Evidence found in kpi_sheet.csv, field_visit_forms.csv supporting measurement: Field visit forms + supervisor summaries.

Key sources: kpi_sheet.csv, field_visit_forms.csv

## Data integrity & audit trail

All referenced sources are copied into `03_SOURCES/` with filenames preserved. The evidence table links each KPI to source filenames.

## Risks / flags

Known gap: Two supervisor summaries missing for November